## Slide 1: Constellation Spirals
Constellation Spiral Definitions
  Spiral 1
    Provide precursor robotic exploration of the lunar environment
    Deliver a lunar capable human transportation system for test and checkout in low Earth orbit
  Spiral 2
    Execute extended duration human lunar exploration missions
    Extend precursor robotic technology demonstrations at Mars
  Spiral 3
    Execute a long-duration human lunar exploration campaign using the moon as a testbed to demonstrate systems (e.g., Lander, habitation, surface power) for future deployment at Mars
  Spiral 4
    Execute human exploration missions to the vicinity of Mars
  Spiral 5
    Execute initial human Mars surface exploration missions
To Meet Spiral Capabilities, Investments are Made in Two Areas: Spiral Systems and Pre-Acquisition Activities
  Spiral Acquisitions
    Systems that Deliver the Spirals End Capability
    For Spiral I Capability of Low Earth Orbit Access, Includes CEV, launch vehicle, etc.
  Pre-Acquisition Activities
    Research, Technology Development, and Flight Demonstrations that Reduce Risk and Provide Technologies for Use by One of the Spiral Systems
    The Customer for Pre-Acquisition Activities are not the End User, but Rather the Systems within a Spiral

## Slide 2
3
Nation’s Vision for Space Exploration

## Slide 4: The Nation’s Vision
1. Return the Shuttle to safe flight as soon as practical, based on CAIB recommendations
2. Use Shuttle to complete ISS assembly
3. Retire the Shuttle after assembly complete (2010 target)
4. Focus ISS research to support exploration goals; understanding space environment and countermeasures
5. Meet foreign commitments
6. Undertake lunar exploration to support sustained human and robotic exploration of Mars and beyond
7. Series of robotic missions to Moon by 2008 to prepare for human exploration
8. Expedition to lunar surface as early as 2015 but no later than 2020
9. Use lunar activities to further science, and test approaches (including lunar resources) for exploration to Mars & beyond
10. Conduct robotic exploration of Mars to prepare for future expedition
11. Conduct robotic exploration across solar system to search for life, understand history of universe, search for resources
12. Conduct advanced telescope searches for habitable environments around other stars
13. Demonstrate power, propulsion, life support capabilities for long duration, more distant human and robotic missions
14. Conduct human expeditions to Mars after acquiring adequate knowledge and capability demonstrations
15. Develop a new Crew Exploration Vehicle; flight test before end of decade; human exploration capability by 2014
16. Separate cargo from crew as soon as practical to support ISS; acquire crew transport to ISS after Shuttle retirement
17. Pursue international participation
18. Pursue commercial opportunity for transportation and other services

## Slide 5
5
Key Elements of the Nation’s Vision
Objectives
  Implement a sustained and affordable human and robotic program
  Extend human presence across the solar system and beyond
  Develop supporting innovative technologies, knowledge, and infrastructures
  Promote international and commercial participation in exploration
Major Milestones
  2008: Initial flight test of CEV
  2008: Launch first lunar robotic orbiter
  2009-2010: Robotic mission to lunar surface
  2011 First Unmanned CEV flight
  2014: First crewed CEV flight
  2012-2015: Jupiter Icy Moon Orbiter (JIMO)/Prometheus
  2015-2020: First human mission to the Moon

## Slide 6: Constellation Spirals
2005
2010
2020
2015
2025
- Crewed Access to Low Earth Orbit
- Robotic Exploration, Lunar
- Crewed Exploration, Lunar Extended Duration
- Robotic Exploration, Mars
Crewed Exploration, Lunar Long Duration
Robotic Exploration, Mars
Other Potential Capabilities
Crewed Exploration, Mars Surface
SPIRAL CAPABILITIES
PRE-ACQUISITION
ACTIVITIES
ESRT
PNST
HSRT
SYSTEM ENGINEERING
ESRT: Exploration Systems Research & Technology
PNST: Prometheus Nuclear Systems Technology
HRST: Human System Research & Technology
TBD
STUDY
DESIGN
STUDY
STUDY
DESIGN
DESIGN
PDR
SRR
STUDY
STUDY
OPERATE
(SOMD)
BUILD, TEST, LAUNCH
BUILD, TEST
BUILD, TEST
COMMERCIAL SOLUTION
BUILD, TEST, LAUNCH
CDR
DESIGN
DESIGN
DESIGN

## Slide 7
8
Program Phases and Milestones NSSAP 0301

## Slide 8: Requirements
Working to Revision B of Exploration Systems Requirements
  Exploration System-of-System Requirements
  Exploration Crew Transport System Requirements
    Spiral I
    Spiral II
    Spiral III
  Crew Exploration Vehicle Concept of Operations
Using NSSAP 03-01 Process, Current Set of Requirements are Basis for Initial Capabilities Document (ICD)
  Requirements Defined to Level of Detail that Supports Concept Studies
  Requirements Will Continue to Mature as Concept Studies Proceed
  Finalized Requirements will be Documented, following Spiral 1 Systems Requirements Review, in an Concept Design Document (CDD) Prior to Entering Design Phase (~2006)
Spiral I Acquisition Strategy for Addressing Requirements
  Ensure Extensibility by Using Future Spirals to Inform Current Development
  Where Feasible, Use Spiral I & II Requirements as Threshold
  Where Feasible, Establish Spiral III Requirements as Goal

## Slide 9: Agenda
Exploration Systems’ Objectives
  Nation’s Vision for Exploration
  Definition of Spirals
  Program Life Cycle Management and NSSAP 03-01
Spiral I Objectives
  Requirements
  Acquisitions within Spiral I
  Pre-Acquisition Activities Supporting Spiral I
FY05 Acquisitions
  CEV RFP
  Commercial Earth to Orbit

## Slide 10
DESIGN
FY 04
FY 06
FY 08
FY 12
FY 14
FY 10
STUDY
DESIGN
STUDY
STUDY
DESIGN
DESIGN
BAA
CEV LV
GROUND SYSTEM
IN-SPACE SYSTEMS
BUILD, TEST, LAUNCH
BUILD, TEST
BUILD, TEST
STUDY
STUDY
CEV
BUILD, TEST, LAUNCH
RFP
Risk Reduction 2008 Demo
OPERATE
(SOMD)
DESIGN
Risk Reduction 2008 Demo
DESIGN
Non Traditional Approach
ETO
POTENTIAL COMMERCIAL SERVICE
CEV: Two Designs to PDR Followed by Downselect
ETO: Alternate Approach Incorporating Commercial Solution
CEV Launch Vehicle: Human Rated Lift
Ground System: Processing, Communications, Command & Control
In-Space Systems: Primarily Communications
PHASE A:
STUDY
PHASE B:
DESIGN
PRE-SPIRAL ACTIVITIES
PHASE C:
BUILD, TEST, LAUNCH
Spiral I Systems: Five Potential Acquisitions
DESIGN

## Slide 11: Spiral I Study Phase
DESIGN
FY 04
FY 06
FY 08
FY 12
FY 14
FY 10
STUDY
DESIGN
STUDY
STUDY
DESIGN
DESIGN
BAA
CEV LV
GROUND SYSTEM
IN-SPACE SYSTEMS
BUILD, TEST, LAUNCH
BUILD, TEST
BUILD, TEST
STUDY
STUDY
CEV
BUILD, TEST, LAUNCH
CDR
RFP
DESIGN
SRR
PDR
PDR
Risk Reduction 2008 Demo
CEV un-crewed
Flight
OPERATE
(SOMD)
DESIGN
Risk Reduction 2008 Demo
DESIGN
ETO
POTENTIAL COMMERCIAL SERVICE
PHASE A:
STUDY
PHASE B:
DESIGN
PRE-SPIRAL ACTIVITIES
PHASE C:
BUILD, TEST, LAUNCH
Spiral I is in Study Phase, 2005-2006
Continue Definition of Requirements
Culminates in System Requirements Review
  Allocation of Spiral Requirements to Individual Elements Complete
  Spiral Requirements Set in Capability Development Document (CDD)
  Evaluate Whether or Not to Continue Non-Traditional ETO Approach
  Design Phase Begins
Non Traditional Approach

## Slide 12: Pre-Acquisition Activities in Support of Spiral I
DESIGN
FY 04
FY 06
FY 08
FY 12
FY 14
FY 10
STUDY
DESIGN
STUDY
STUDY
DESIGN
DESIGN
BAA
CEV LV
GROUND SYSTEM
IN-SPACE SYSTEMS
BUILD, TEST, LAUNCH
BUILD, TEST
BUILD, TEST
STUDY
STUDY
CEV
BUILD, TEST, LAUNCH
CDR
RFP
DESIGN
SRR
PDR
PDR
Risk Reduction 2008 Demo
CEV un-crewed
Flight
OPERATE
(SOMD)
DESIGN
Risk Reduction 2008 Demo
DESIGN
Non Traditional Approach
ETO
POTENTIAL COMMERCIAL SERVICE
PHASE A:
STUDY
PHASE B:
DESIGN
PRE-SPIRAL ACTIVITIES
PHASE C:
BUILD, TEST, LAUNCH
Spiral I Technology Infusion
  Content Determined by Gap Analysis of Capabilities Against Requirements
  Technologies Targeted for Transition at CEV PDR
Safety Net
  Final Adjustment in Portfolio
  Fill Technology Areas Left Uncovered by Previous Competitions
System Integrator
  Strategy Still in Development
  Planning for RFP in Late FY05
ESRT/HSRT EFFORTS
Technology Infusion BAA
BAA
SYSTEM ENGINEERING AND INTEGRATION
S. Integrator
RFP
ESRT/HSRT RESEARCH
Safety Net ICP
ICP

## Slide 13: Agenda
Exploration Systems’ Objectives
  Nation’s Vision for Exploration
  Definition of Spirals
  Program Life Cycle Management and NSSAP 03-01
Spiral I Objectives
  Requirements
  Acquisitions within Spiral I
  Pre-Acquisition Activities Supporting Spiral I
FY05 Acquisitions
  CEV RFP
  Commercial Earth to Orbit

## Slide 14: CEV Development Plan
INDUSTRY
INPUTS
FY 2005
FY 2006
FY 2008
FY 2009
FY 2007
FY 2004
2014
REV A
CONTINUING REFINEMENT
CONCEPT DEV
DESIGN DEVELOPMENT
RISK REDUCTION VIA 2008 DEMONSTRATION
CONCEPT DEV
DESIGN DEVELOPMENT
DOWN
SELECT
ACQUISTION AND
OPERATION
PHASE A:
STUDY
PHASE B:
DESIGN
PRE-PHASE A ACTIVITIES
PHASE C:
BUILD, TEST, LAUNCH
SRR
PDR
SRR
PDR
MS A
MS B
MS C
CEV RFP
SOURCE SELECTION
CEV CONTRACT
GOVT
INPUTS
C
HUMAN RATED LAUNCH VEHICLE SYSTEM ACQUISITION
GROUND SYSTEM ACQUISITION
OTHER REQUIRED ACQUISITIONS
ALLOCATED
REQUIREMENTS
B
SPIRAL I ACQ.
STRATEGY
Development Plan
Contracting
Risk
Budget/Cost
RFP
Development
SOO/SOW
Clauses
Selection Plan
PROGAM DEVELOPMENT
REQUIREMENTS
DIRECTORATE
MILESTONES
RISK REDUCTION VIA 2008 DEMONSTRATION

## Slide 15: CEV Development Plan
Purpose: Develop Capability for Crewed Access to Space
  LEO Access by 2014 (Threshold)
  Provide Capability for Extended Lunar Exploration (Threshold)
  Provide Capability for Long Lunar Exploration (Objective)
Development Plan
  Pre-Phase A (3rd Quarter FY04 to 2nd Quarter FY05)
    Integrate Independent Government/Industry Analysis of Requirements
    Determine Functional Requirements for the Combined CEV/Launch Vehicle/Ground System
  Phase A: Study Phase (3rd Quarter FY05 to 4th Quarter FY06)
    Award Two CEV Contracts with Two Objectives
      Spiral I Architecture and Functional Requirements Analysis/CEV Design
      Risk Reduction Demonstration for 2008
    At SRR, Allocate Individual Requirements for CEV, Launch Vehicle, Ground System, Etc.
  Phase B: Design (1st Quarter FY07 to 3rd Quarter FY08)
    Continue with Two Contractors into CEV Design Phase
    After PDR and 2008 Demonstration, Downselect to Single CEV Developer
  Phase C: Build, Test, Launch (1st Quarter FY09 to 4th Quarter FY14)

## Slide 16: Fee Structure
Award Fee
  Fee Based on Contractor Compliance to Their Proposed Baseline
    After Contract Award, Conduct Integrated Baseline Review (IBR)
    Percentage of Award Based on Contractor Meeting Schedule and Cost
    Possibly use SPI and CPI as Metric
  Fee Allocation by Milestone Events
    IBR, Initial Baseline Review
    SRR, System Readiness Review
    PDR, Preliminary Design Review
    Completion of 2008 Demonstration
  Unallocated Fee Can be Rolled Forward to Next Award Period at Program Manager’s Discretion
Fee Amount of 10-15% of Contract Value

## Slide 17: Down Select and Period Of Performance
Two Options Under Consideration
Single RFP to 2014
  Set up with Phase I/Phase II
  Phased Downselect in 2008
Two RFPs
  First RFP: Study/Design Phase (2005-2008)
  Second RFP: Design/Build-Test-Fly (2008-2014)
For Either Approach
  Demonstration is for Risk Reduction and “Past Performance” Data
  Demonstration is not a Flyoff
  Anticipate that Competition will be Limited to Two Contractors Performing Under First Contract/Phase I
The government contemplates that viable and effective competition will be restricted to firms performing CEV contracts through flight demonstration. Firms not performing under NASA CEV contracts for Phase A/B, and opting to submit proposals for Phase C-E, will be required to submit PDR and flight demonstration "equivalent" packages to illustrate ability to successfully execute CEV deployment to low earth orbit in 2014.

## Slide 18: Commercial Approach for Earth to Orbit
Objective
  Pursue High Risk, High Payoff Strategy for Earth to Orbit (ETO) Access
Strategy
  Use Space Act, Cooperative Agreement, Other Transaction, or other Partnering in Lieu of Traditional FAR Contract
  Evaluate Progress Concurrent with System Requirements Review (2006) and Preliminary Design Review (2008)
  If Commercial Solution Proves Viable, Then Descope CEV and CEV Launch Vehicle Requirements Accordingly
  Regardless of Success of Commercial ETO, CEV Acquisition will Continue with appropriately descoped or adjusted requirements
Schedule
  Decision on Whether or Not to Pursue a Commercial Solution will be Made Prior to Release of Draft CEV RFP (Jan 2005)
  If Decision is Made to Pursue, Anticipate Solicitation in FY05

## Slide 19: Conclusions
Acquisition Strategy is a Work in Progress
Expect Release of Draft Statement of Work for Comment in Early December
Continuing on Schedule for CEV RFP Release in March 2005
NASA will Post Periodic Updates to the Website at http://www.exploration.nasa.gov

## Slide 20: Launch Vehicle
Objective
  Pursue human rated launch vehicle to support CEV with potential evolution into cargo and heavy lift missions
Strategy
  Pre-Phase A (3rd Quarter FY04 to 3nd Quarter FY05)
    Integrate Independent Government/Industry Analysis of Requirements
    Determine Functional Requirements for the Combined CEV/Launch Vehicle/Ground System
  Phase A: Study Phase (4rd Quarter FY05 to 4th Quarter 2006)
    Using BAA Award multiple Launch System Contracts to:
      Provide Launch system requirements and concept support
      Coordinate with CEV contractors and System Integrator in the allocation of individual requirements for CEV, Launch Vehicle, Ground System, Etc.
      Support Spiral 1 level System Requirements Review
  Phase B/C: Competitive award to complete Design (FY07)
    Contract structure and scope to be developed during Phase A
Schedule
  Draft RFP Release 2nd-3rd Quarter FY05
  Contract award Phase A 4th Quarter FY05
  Launch Vehicle Design phase commence FY07 following Spiral 1 System Requirements Review

## Slide 21: System Integrator
Objective
  Create a Government/Industry team to provide systems engineering & integration functions necessary to complete the integration of complex multi-element systems
Strategy
  Government team will provide systems engineering & integration functions necessary to complete Spiral 1 System-of-Systems design through SRR in FY2006(3rd Q)
  Government retains Total System Performance Responsibility
  Contractor team will ramp up through Spiral 1 SRR and support Spiral 2 Pre-Phase A systems engineering functions
Schedule
  Contract Award ~January 2006

## Slide 22: Spiral I Technology Infusion
Objective
  Technology infusion addressing key needed technologies for CEV and Spiral 1
Strategy
  BAA Solicitation to be enabled through coordination with / input from Requirements Division, CE&R project activities and others (Technical Interchange Meeting planned for mid-December
Schedule
  BAA to be issued in 2nd Quarter FY 2005

## Slide 23: Safety Net BAA
Objective
  Addresses important missing technology areas, competency gaps, etc.
Strategy
  Acquisition strategy still in development; requires close coordination with NASA Field Centers
Schedule
  3rd Quarter FY 2005